## Introduction
Project Name
What is this? | This workbook is meant to help manage and piroritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## Product backlog
Project Name
| Organizations | CS492 Group 5
| Project | Pizza Restaurant Online Ordering System
| Product Owner | Mark Legaspi
| Scrum Master | Jacob Lenz
| Development Team | Felicia Mach, Garret Thompson, Risa Luthor
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
1 | Welcome Page | Includes Pizzeria company name, promotions, discounts | Must have pizzeria's company name, short description of pizzeria's history as a company, list of promotions and discounts that the pizzeria is having | 1 | 1 | Product Owner and Scrum Master, Developer Team
2 | User Registration | Allow customers to create an account by providing basic information (name, email, password) | User can successfully register, password must meet security requirement (e.g., minimum length, complexity), Confirmation email sent for account verification. | 1 | 1 | Developer Team
4 | Contact Info Page | Includes contact info. of pizzeria | Must include pizzeria's address, phone number, fax number, etc. | 2 | 1 | Product Owner and Scrum Master, Developer Team
5 | Menu Browsing | Customers can view the restaurant's menu, including descriptions and prices. | Menu items are categorized (e.g., pizza, sides, drinks), each item displays name, description , and price. | 1 | 1 | Product Owner and Scrum Master
6 | Adding Items to Cart | Customers can select menu items, customize their orders (e.g., toppings, crust type), and add them to the cart | Users can add items to the cart, Customization options (e.g., toppings) are available, Quantities can be adjusted. | 1 | 1 | Product Owner and Scrum Master, Developer Team
7 | Shopping Cart | Will store menu items placed in it | Must store items, allow editing quantity, remove items, empty cart, and current total | 1 | 1 | Product Owner
8 | Order Confirmation Page | Includes pizzas that were selected to order | Must have list of pizzas choosen for orders to be sent to pizzeria, includes pricing of all pizzas, total amount, discounts/promotions are included into price | 1 | 1 | Product Owner and Scrum Master, Developer Team
9 | Payment | Includes payment options for credit card or pay in store | Must have types of credit card options for customer to choose from, pay in store option for customers to send to the order in ahead of time and pay during pick-up | 1 | 1 | Product Owner and Scrum Master, Developer Team
12 | SQL Database | Database to retain menu items and accounts | Must store all menu items, inventory totals, and user accounts. Passwords must be stored encrypted | 1 | 1 | Scrum Master
13 | Payment Security | Implement secure payment gateways to protect customer financial information. | Payment processing complies with industry security standards (e.g. PCI DSS), Regular security assessments and audits are conducted. Uses third party payment processing | 2 | 2 | Developer Team
14 | Data Encryption | Implement encryption techniques to protect client data such as payment and password information. | User data is stored securely using industry-standard encryption algorithms, Sensitive information is never stored in plain text. | 2 | 2 | Developer Team
15 | Store Manager Dashboard | The store manager can access a dashboard to manage the menu in real-time. | Dashboard provides access to menu management features, Manager can add new items, update prices, and enable/disable items. | 2 | 2 | Product Owner and Scrum Master
16 | Inventory Integration | The menu reflects real-time inventory availability. | Items are automatically marked as unavailable when out of stock. | 2 | 2 | Product Owner and Scrum Master, Developer Team

## Sprint 1
Sprint #1Tracking Sheet
|  | Project |  | Pizza Restaurant Online Ordering System
|  | Sprint # |  | 1
|  | Start date |  | 2023-10-03
|  |  | Total Team Members | 3
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16
MTG | N/A | Scrum Meeting | Scrum Master, Product Owner and Developer Team | 1 | 2023-10-05: 1.5; 2023-10-07: 0.5
1.1 | 1 | Welcome Page (Create pizzeria logo) | Product Owner | 2 | bar: 2023-10-03
1.2 | 1 | Welcome Page (Create landing page) | Product Owner | 2 | 2023-10-04: 0.5; 2023-10-06: 1; 2023-10-13: 0.5
2.1 | 2 | User registration - Create registration form UI | Developer Team | 1 | 2023-10-06: 1; 2023-10-14: 2
2.2 | 2 | User registration - Implement user registration logic | Developer Team | 2 | 2023-10-07: 1; 2023-10-08: 1; 2023-10-15: 1.5
2.3 | 2 | Authentication - Implement password encryption | Developer Team | 1 | 2023-10-09: 0.25; 2023-10-15: 0.5
4.1 | 4 | Contact Info (Create tab/link on buttom of page next to Reviews for easy access) | Developer Team | 2 | 2023-10-06: 1; 2023-10-07: 0.5; 2023-10-08: 0.5
5.1 | 5 | Menu presentation - Design menu categories | Product Owner and Scrum Master | 1 | 2023-10-10: 0.5; 2023-10-12: 0.5; 2023-10-13: 0.5
5,2 | 5 | Menu presentation - Implement menu item display | Product Owner and Scrum Master | 1 | 2023-10-12: 1; 2023-10-15: 0.5
5.3 | 5 | Menu presentation - Create basic menu UI | Scrum Master and Developer Team | 1 | 2023-10-11: 0.5; 2023-10-12: 0.5; 2023-10-14: 0.5
6.1 | 6 | Adding Items to cart - Develop "Add to Cart" button functionality | Scrum Master, Product Owner and Developer Team | 2 | 2023-10-14: 2
6.2 | 6 | Adding Items to cart - Create customization options UI | Scrum Master and Developer Team | 1 | 2023-10-14: 0.5
6.3 | 6 | Adding Items to cart - Implement cart update logic | Developer Team | 2 | 2023-10-14: 0.5
7.1 | 7 | Create shopping cart logic | Product Owner | 1 | bar: 2023-10-14
8.1 | 8 | Order Confirmation Page (Create separate page for ready to pay orders) | Scrum Master and Developer Team | 5 | 2023-10-13: 2
9.1 | 9 | Payment Page (Create selection of payment option) | Product Owner and Developer Team | 5 | 2023-10-13: 0.5
12.1 | 12 | Create database for web site | Scrum Master | 0.5 | 2023-10-08: 0.5
12.2 | 12 | Create tables and relationships within database | Scrum Master | 1 | 2023-10-08: 0.5
12.3 | 12 | Populate database witrh intial values | Scrum Master | 1 | 2023-10-08: 0.5
MTG | N/A | Sprint Review Meeting | Scrum Master, Product Owner and Developer Team | 1 | 2023-10-15: 1.5
|  | Remaining units (actual) |  | 48 | 47 | 46.5 | 45 | 42 | 40 | 37 | 36.75 | 36.25 | 35.75 | 33.75 | 30.25 | 23.75 | 19.75 | #N/A
|  | Remaining units (ideal) |  |  | 44.5714 | 41.1429 | 37.7143 | 34.2857 | 30.8571 | 27.4286 | 24 | 20.5714 | 17.1429 | 13.7143 | 10.2857 | 6.8571 | 3.4286 | 0

## Sprint 2
Sprint #2Tracking Sheet
|  | Project |  | Pizza Restaurant Online Ordering System
|  | Sprint # |  | 2
|  | Start date |  | 2023-10-17
|  |  | Total Team Members | 3
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30
MTG | N/A | Beginning of Sprint Meeting | Product Owner and Scrum Master, Developer Team | 1 | bar: 2023-10-19; 2023-10-26
13.1 | 13.1 | Create page to take payment input | Product Owner | 1 | 2023-10-21: 0.5; 2023-10-22: 0.5
13.2 | 13.2 | Create logic to use third party API to securely process paymeny | Product Owner and Developer Team | 1.5 | 2023-10-20: 1; 2023-10-23: 0.25
14.2 | 14.1 | Encrypt passwords in database | Scrum Master and Developer Team | 1 | 2023-10-21: 0.25
14.3 | 14.2 | Restrict database access via accounts | Scrum Master and Developer Team | 1 | bar: 2023-10-20 to 2023-10-21
15.1 | 15.1 | Management dashboard - Design store manager dashboard UI | Developer Team | 1 | 2023-10-17: 2.5; 2023-10-19: 1
15.2 | 15.2 | Management dashboard - Develop menu item management functionality | Product Owner and Scrum Master | 2 | bar: 2023-10-17 to 2023-10-18
15.3 | 15.3 | Management dashboard - Implement pricing update feature | Product Owner and Scrum Master | 2 | 2023-10-19: 2
16.1 | 16.1 | Inventory Integration - Integrate with inventory system | Product Owner and Scrum Master, Developer Team | 1 | 2023-10-22: 0.5
16.2 | 16.2 | Inventory Integration - Develop automatic item status update logic | Product Owner and Scrum Master, Developer Team | 2 | 2023-10-25: 1; 2023-10-27: 0.5
T.1 | N/A | Team code review of whole project | Product Owner and Scrum Master, Developer Team | 2 | 2023-10-19: 0.25; 2023-10-21: 0.25
T.2 | N/A | Test every aspect of the web site | Product Owner and Scrum Master, Developer Team | 2 | 2023-10-18: 0.5; 2023-10-21: 0.25; 2023-10-28: 0.5; 2023-10-29: 0.5
T.3 | N/A | Proofread web stie | Product Owner and Scrum Master, Developer Team | 1 | 2023-10-21: 0.25; 2023-10-24: 0.25; 2023-10-29: 0.5
MTG | N/A | Sprint review meeting | Product Owner and Scrum Master, Developer Team | 1 | 2023-10-29: 0.5
MTG | N/A | Project review meeting | Product Owner and Scrum Master, Developer Team | 1 | 2023-10-29: 0.5
|  | Reviews Section | Developer Team | 1 | bar: 2023-10-22
|  | Remaining units (actual) |  | 48 | 44.5 | 43 | 38.75 | 36.75 | 34.25 | 32.25 | 32 | 31.75 | 30.75 | 29.75 | 29.25 | 28.75 | 26.75 | #N/A
|  | Remaining units (ideal) |  |  | 44.5714 | 41.1429 | 37.7143 | 34.2857 | 30.8571 | 27.4286 | 24 | 20.5714 | 17.1429 | 13.7143 | 10.2857 | 6.8571 | 3.4286 | 0